## Sheet1
https://goo.gl/PXLbMe
Battle Bots | [5 empty] | UCF
PROJECT MANAGER | [5 empty] | Fall 2022
[6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (days) | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Project task assignment |  |  |  |  | 0% | bar: WEEK 1 T to WEEK 1 R
Gantt chart |  |  |  |  | 0% | bar: WEEK 1 F to WEEK 2 T
Decide on cohort group |  |  |  |  | 0% | bar: WEEK 2 W
Research |  |  |  |  | 0% | bar: WEEK 2 W to WEEK 3 W
Projections |  |  |  |  | 0% | bar: WEEK 2 R to WEEK 3 R
Weekly Report #4 |  |  |  |  | 0% | bar: WEEK 3 M to WEEK 3 R
Statement of work (individual) |  |  |  |  | 0% | bar: WEEK 3 T to WEEK 3 R
Statement of work |  |  |  |  | 0% | bar: WEEK 3 R to WEEK 3 F
Weekly Report #5 |  |  |  |  | 0% | bar: WEEK 3 F
KEY FEATURE # 1 (Interaction)
UI for selecting robot |  |  |  |  | 0% | bar: WEEK 4 M to WEEK 5 T
Controlling the robot |  |  |  |  | 0% | bar: WEEK 4 T to WEEK 5 T
Spawn robot after selection |  |  |  |  | 0% | bar: WEEK 4 T to WEEK 5 T
More Ideas before finalizing first key feature in Root |  |  |  |  | 0% | bar: WEEK 4 W to WEEK 5 W
Seed prototype |  |  |  |  | 0% | bar: WEEK 4 R to WEEK 5 R
Weekly Report #6 |  |  |  |  | 0% | bar: WEEK 4 F to WEEK 5 F
Weekly Report #7 |  |  |  |  | 0% | bar: WEEK 5 M to WEEK 6 M
Polish Key feature #1 if already completed |  |  |  |  | 0% | bar: WEEK 5 M to WEEK 6 M
Decide on a new key feature if messed up on the seed prototype |  |  |  |  | 0% | bar: WEEK 5 T to WEEK 6 T
Root prototype |  |  |  |  | 0% | bar: WEEK 5 T to WEEK 6 T
Weekly Report #8 |  |  |  |  | 0% | bar: WEEK 5 T to WEEK 6 T
Weekly Report #9 |  |  |  |  | 0% | bar: WEEK 5 W to WEEK 6 W
KEY FEATURE # 2 (Scenario)
Different weapons: flipper, blade, cannon |  |  |  |  | 0% | bar: WEEK 7 M to WEEK 7 R
Traps: spinning blade, pits, flipper |  |  |  |  | 0% | bar: WEEK 7 T to WEEK 8 T
Damagable Parts: pizza (main body), rectangle (wheels, body), triangle (wheels, blade) |  |  |  |  | 0% | bar: WEEK 7 T to WEEK 8 T
Match Outcome: 0 hp, knocking out map |  |  |  |  | 0% | bar: WEEK 7 T to WEEK 8 T
Trunk Prototype |  |  |  |  | 0% | bar: WEEK 7 W to WEEK 8 W
Weekly Report #10 |  |  |  |  | 0% | bar: WEEK 7 R to WEEK 8 R
Weekly Report #11 |  |  |  |  | 0% | bar: WEEK 7 F to WEEK 8 F
KEY FEATURE # 3 (Backend) |  |  |  |  | 0%
Photon Setup |  |  |  |  | 0% | bar: WEEK 10 M to WEEK 11 M
Unity networking |  |  |  |  | 0% | bar: WEEK 10 M to WEEK 11 M
Branch Prototype (Individual) |  |  |  |  | 0% | bar: WEEK 10 T to WEEK 11 T
Branch Prototype |  |  |  |  | 0% | bar: WEEK 10 T to WEEK 11 T
Weekly Report #12 |  |  |  |  | 0% | bar: WEEK 10 T to WEEK 11 T
Weekly Report #13 |  |  |  |  | 0% | bar: WEEK 10 W to WEEK 11 W
Weekly Report #14 |  |  |  |  | 0% | bar: WEEK 10 R to WEEK 11 R
Crown Prototype (Individual) |  |  |  |  | 0% | bar: WEEK 10 F to WEEK 11 F
Crown Prototype |  |  |  |  | 0% | bar: WEEK 11 M to WEEK 12 M
Weekly Report #15 |  |  |  |  | 0% | bar: WEEK 11 M to WEEK 12 F